## Sheet1
Project Name | [7 empty] | 2026-01-01
Project manager name and contact | [7 empty] | 2026-12-31
Stage title | Start | End | Duration (days) | Schedule | Responsible | Budget | Risks | Comments
Project Initiation | 2026-01-01 | 2026-02-04 | 35 | Completed | Jane Smith | 5000 | Misalignment on goals | Kick-off meeting completed
Research & Requirements | 2026-01-05 | 2026-02-16 | 43 | In progress | Michael Johnson | 8000 | Incomplete stakeholder feedback | Waiting for final client input
Design Phase | 2026-03-04 | 2026-06-10 | 99 | Delayed | Sarah Lee | 12000 | Possible delays due to revision cycles | Wireframes approved, UI in progress
Development Phase | 2026-03-02 | 2026-11-05 | 249 | On hold | Dev Team | 40000 | Unexpected technical issues | Backend API documentation pending
Testing & QA | 2026-01-07 | 2026-05-08 | 122 | On hold | QA Team | 6000 | Bugs may require rework | Test plan will be finalized in November
Launch & Marketing | 2026-06-09 | 2026-11-19 | 164 | Not started | Marketing Dept. | 10000 | Poor rate if campaign is delayed | Launch date to be confirmed w. client
Project Closure | 2026-09-23 | 2027-01-01 | 101 | Not started | Jane Smith | 2000 | Delays in final reporting | Prepare final report and feedback
Enter text |  |  | 1 |  |  | 0
Enter text |  |  | 1 |  |  | 0
Enter text |  |  | 1 |  |  | 0
Enter text |  |  | 1 |  |  | 0
Enter text |  |  | 1 |  |  | 0
Enter text |  |  | 1 |  |  | 0